## Sheet1
Task | Sub Task | Estimated duration | Complexity | Owner(s) | Assumptions, Comments
Site analysis and preparation | Review the current site, and collect:
Design documentation
Use cases
Custom code
Review the new features and changes made in HCL Commerce 9.0.
| Gather new requirements |  |  |  |  | `
Review deprecated and removed APIs and determine how you are going to address each one.
Review all custom scripts that are used for tasks such as build, deployment, or data load.
If you have previously customized Management Center, review any changes that affect your customizations and determine how you are going to address each one.
If you have connections to external systems, you need to ensure that there are test stubs / test connections available for your migration team to use.
Review traffic statistics for your site and project statistics for the future. Use this analysis to determine if you are going to need to purchase new hardware. Procuring hardware can take time, and you want to include this in your project plan.
Technical staff education | Education on how to utilize the new CI/CD pipeline.
Education on how to plan and execute your container infrastructure.
Education on developing with JPA technology.
Build your container platform and CI/CD pipeline | Determine which software you want to use to build a container platform that can support the HCL Commerce application.
Create your strategy for frequently deploying new features, updates, or fixes to your production environment.
Implement your container platform and CI/CD pipeline, including your staging and production environments.
Configure the HCL Commerce Build (WCB) tool.
Development environment migration | On an existing HCL Commerce Developer installation, perform a regression test of all custom code to ensure that there is no confusion as to what the source of problems are after migration is complete.
Ensure that you meet all prerequisites.
Install and configure HCL Commerce Developer.
Migrate site your security, configurations. Then, migrate the development database.
Migrate your remaining assets (make a new row for each custom asset, or create a new document to track all custom assets). For example, the most time consuming tasks tend to be:
Fixing deprecation and compilation warnings
EJB to JPA migration
Store migration
Search migration
Test the migrated application in the development environment.
Build your migrated custom assets by using the WCB tool and deploy your assets to your HCL Commerce application. Then, test your custom assets within your production environment.
Production server migration | Take a backup of your version 7.0 or 8.0 production database, then restore the version 7.0 or 8.0 production database copy on version 9.0 production environment.
Migrate the restored/offline database.
Test your migrated customizations at runtime against the offline database while tuning for production site traffic volumes.
Back up live version 7.0 or 8.0 database.
Point your version 9.0 environment to the live version 7.0 or 8.0 database.
Migrate the live database while still serving traffic.
Switch traffic from version 7.0 or 8.0 environment to version 9.0 environment.
Update SITE table on live database.
Test the migrated site
Get education for the day to day maintenance
Post launch support
Project management
Contingency (for unknown or unexpected issues)
Total project hours:

## Sheet2
S.NO | Task | Sub Task | Estimated duration(Hours) | Complexity | Owner(s) | Assumptions, Comments | Status
1 | Actions to undertake before the migration. | Take the backup of all entities data | 1 | Easy |  | As there are more than 10000 entities for each entity type,all the data of entities can be taken in only CSV format. It cannot be downloaded through excel
|  | Take the backup of current module of the system | 4 | Medium |  | As some of the functionalities of DS may get impacted after migration, it is required to take the backup ofncurrent module of DS.
|  | Take the backup of DS environment | 5 | Medium |  | As the existing data of DS may get impacted after migration, it is required to take the backup of DS .
|  | Data Clean-up of Petsupermarket DS Environment data | 4 | Medium |  | Delete all the data at petsuprmarket DS Environment.
|  | Make some of the attributes from single valued to multivalued and merge existing data | 6 | Medium |  | We have to merge data of duplicate attributes and place them in the primary attribute(e.g: Primary pet type, pet type 1, pet type 2). While performing this requirement on a large number of entities(bulk upload), some of the BRs functionality may effect.
|  | Change the display names for some of the attributes. | 2 | Easy |  | As there are different display names in dev and prod, it creates impact on data while loading the data
2 | Impact analysis on data | Disable the non-required BR's during the migration. | 4 | Medium |  | Once we enable the BRs after migration, some of the attributes values which are dependent on other attribute's will differ
|  | Disable the non-required Graphs during the migration. | 4 | Medium |  | Enabling graphs may add extra relationships to some of the entities
|  | Thing data validations | 4 | Medium |  | It will throw an error at attribute level
|  | List out the Impacted attributes (Data type changed attributes) | 2 | Easy |  | It will results as invalid data( Ex: Shipping Height changed from string to decimal in dev. Now ,DS will not accept any other alphabets and special characters except numerics and decimals)
3 | Migration | Loading the data to DS environment (In a single file 2000 entities) in an hour. | 18 | high-Complex |  | If we upload more than 2000 entities at a time, it will create load on the system.
|  | Enable the relationship BR's(Form the relationship between the Product and SKU) | 5 | Medium |  | To form the relationship between the product and SKU during migration.
4 | Data correction after Migration | Impact on workflows (Required attributes Business Condition data corrections for 30k entities) | 8 | Complex |  | Due to the addition of new required attributes, entities will stuck in New SKU introduction workflow.
|  | Entity data validations | 6 | Medium |  | To check and correct the invalid data at attribute level of entities.
|  | Total Hours (Appox) | 73